## Gantt Chart
|  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
| Timeline | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
Foundations | 1.0 Supervisor Meetings 6x30 min
1.0 Online e-Modules
1.1 Read and answer supplied educational scenarios
1.1 Brief Essay philosophy of teaching and learning
1.2 Complete personal learning plan that fills gaps not covered by CE units
1.2 Medical Education Conference
1.3 Perform a CE consultation and obtain feedback on it
1.4 Become involved in Community of practice, dialogue or activites related to educational interest
Teaching & Learning | 2.0 Need to complete six hours of formal learning
2.0 Need to have 4 x 30 minute meetings supervisors
2.1 Reflective Essay instructional methods for three different learning environments
2.1 Submit teaching evaluations from 5 learners pertaining to at least 2 different teaching methods
2.1 Submit teaching evaluations from two peers using at least 2 different teaching methods
2.2 Submit a de-identified record of summative feedback to a learner (letter from student)
2.2 Submit a written report regarding formative feedback encounters
Curriculum | 3.0 Complete 6 hours of formal learning
3.0 need four 30 min meetings with supervisor meetings
3.1 Report outlining a needs assessment for a planned curriculum or curricular innovation
3.2 Design and plan implementation of curriculum based on the above needs assessment. Written report required
5.1 Plan/desgin a program evaluation for planned curriculum to determine strengths and limitations. Written report required
Assessment | 4.0 Complete 6 hours formal learning
4.0 need four 30 minute meetings
4.2 Written essay or report about active involvement in the development/improvement and implementation of a system assessment
4.1Write an essay or multimedia report on the developmemnt or improvement of a system of assessment for a program (clerkship)
4.3 Write a reflective report on self assessment based on a life long learning activity
Program Evaluation | 5.1 - Program Evaluation plan - FOLDED INTO Curriculum (and optionally crosses over with Education Scholarship)
Education Leadership | 6.0 need to complete 6 hours of learning
6.0 need to complete four 30 min meetings with supervisor
6.1 lead a team with the goal of completing an education project, reflective essay needed after
6.1 Complete a personal leadership inventory
6.3 etablish a formal relationship with at least one mentor and reflect on this, essay required
6.1 Reflective essay or multimedia report discussing the candidates philosophy of leadership and linking it to the challenges of actually leading a team etc.
6.2 A summative report by the candidate that demonstrates incorporation of feedback from members of team
6.3 Submit a letter from a mentor indicating that formal relationship has been established.
Education Scholarship | 7.1 (also can overlap with 5.1 from curriculum) A design for an education scholarship project
7.2 A standard current curriculum vitae that emphasizes the candidate’s scholarly contributions
7.3 A reflective report (academic essay or multimedia report) describing how education scholarship aligns with the candidate’s teaching and/or educational leadership role(s)
7.4 Final Unit Report: a narrative report from the unit advisor using the prescribed template indicating that the candidate has successfully completed the unit
Simulation | 8.0 need to complete 6 hours formal learning
8.0 four 30 minute supervisor meetings required
8.1 self designed simulation based learning activity including development and evaluation of learning activity in simulatio. Documentation needed
8.2 video portfolio needed with a minimum of 3 conducted debriefings that include specific criteria
8.2 essay or multimedia report reflecting my approach to debriefing
8.3 essay or multimedia report that evaluates the simulation based learning activity, needs a generic accepted framework

## Learning Hours Tracker
| Activity | Duration Required | Duration Attended) | Date completed | URL to event if possible | Do you have a formal attendance receipt (CME certificate)? | Do you have a PDF of conference program?
Foundations | Supervisor Meeting 1 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 2 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 3 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 4 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 5 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 6 | 30 min |  |  | N/A | N/A | N/A
| e-Modules | As needed
| Attend a MedEd Conference | at least 1 day
Teaching & Learning | Supervisor Meeting 1 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 2 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 3 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 4 | 30 min |  |  | N/A | N/A | N/A
| Formal Learning | Needs to total 6 hours
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Curriculum | Supervisor Meeting 1 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 2 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 3 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 4 | 30 min |  |  | N/A | N/A | N/A
| Formal Learning | Needs to total 6 hours
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Assessment | Supervisor Meeting 1 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 2 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 3 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 4 | 30 min |  |  | N/A | N/A | N/A
| Formal Learning | Needs to total 6 hours
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Education Leadership | Supervisor Meeting 1 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 2 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 3 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 4 | 30 min |  |  | N/A | N/A | N/A
| Formal Learning | Needs to total 6 hours
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Education Scholarship | Supervisor Meeting 1 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 2 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 3 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 4 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 5 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 6 | 30 min |  |  | N/A | N/A | N/A
Simulation | Supervisor Meeting 1 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 2 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 3 | 30 min |  |  | N/A | N/A | N/A
| Supervisor Meeting 4 | 30 min |  |  | N/A | N/A | N/A
| Formal Learning | Needs to total 6 hours
Formal Learning
Formal Learning
Formal Learning
Formal Learning
Formal Learning